## Master Checklist
CôBa's Daughter × Glossy — September 2026 Master Checklist
Two events: Glossy Pop NYC gift bags (Sep 11, FIT) + Glossy Campus Game Day booth, UT Austin (Sep 12). All costs are estimates — confirm before ordering.
LEGEND — blue text: editable inputs (qty, unit cost, owner, dates). Yellow fill: placeholder to confirm (Buyer/Finance/Glossy). Black: formulas, do not type over. Add rows in the spare section; Total column recalculates.
Item | Event | Category | Qty | Unit Cost ($) | Total ($) | Cost Type | Owner | Source / Vendor | Delivery Route | Due | Status | Notes
Miniset — current version (Plan B) | NYC Pop | Product | 100 | 7 | 700 | Inventory COGS | Head of Products | Amazon AWD warehouse | AWD removal → NYC helper address | Aug 22 | Not started | Unit cost = placeholder COGS, Finance to confirm. Superseded if Plan A miniset lands in time.
Aloe Gel full-size (Plan B, gift bags) | NYC Pop | Product | 100 | 8.5 | 850 | Inventory COGS | Head of Products | Amazon AWD warehouse | AWD removal → NYC helper address | Aug 22 | Not started | Placeholder COGS. Pairs with current miniset under Plan B.
NEW miniset w/ loofah scrub (Plan A) | NYC Pop | Product | 100 | 0 | 0 | Inventory COGS | Buyer team | VN production | Sea/air → NYC (gate: must land by Sep 4) | Jul 24 gate | Awaiting Buyer | GATE: Buyer lead-time answer by Jul 24. If landed-by-Sep-4 impossible → execute Plan B rows above. Unit cost TBD.
Aloe Gel full-size (game-day gifts) | Game Day | Product | 50 | 8.5 | 425 | Inventory COGS | Head of Products | Amazon AWD warehouse | AWD removal → Austin house | Aug 29 | Not started | Post-and-tag reward, capped/day. Placeholder COGS.
Canvas drawstring bag, logo 1-color print | NYC Pop | Packaging | 110 | 2.9 | 319 | Cash | Brand Director | US promo supplier (4imprint / Totally Promotional) | US ship → NYC helper | Aug 28 | Not started | 100 bags + 10 spares. Get 2 quotes; US supplier only (no intl lead-time risk).
Tissue paper + ribbon fillers | NYC Pop | Packaging | 1 | 40 | 40 | Cash | NYC helper | Amazon US | US ship → NYC helper | Aug 28 | Not started | Brand-adjacent colors: cream / kraft.
Voucher booklet (perforated, binder-style) | NYC Pop | Printing | 100 | 1.7 | 170 | Cash | Brand Director | US print (Vistaprint / local NYC) | US ship → NYC helper | Aug 28 | Not started | Unique codes per booklet if possible → per-bag attribution.
Brand book, compact print | NYC Pop | Printing | 100 | 1 | 100 | Cash | Brand Director | US print OR handcarry (Sao & Eva) | US ship or handcarry | Sep 8 | Not started | Compare: US print vs VN print + handcarry. Handcarry saves cash but adds luggage.
Fortune ticket cards (quẻ), 500 pcs | Game Day | Printing | 1 | 90 | 90 | Cash | Brand Director + Emma | Austin print shop | Local pickup (Emma) | Sep 5 | Not started | Western 'lucky ticket' design; voucher QR on back. Includes ~30 fortune texts.
Numbered fortune sticks (craft dowels + numbering) | Game Day | Printing | 100 | 0.4 | 40 | Cash | Emma | Craft store Austin + DIY numbering | Local (Emma) | Sep 5 | Not started | Wood craft dowels; number stamp or burnt-orange dip ends.
Easels for brand panels | Game Day | Booth & Ops | 7 | 15 | 105 | Cash | Emma | Amazon US | US ship → Austin house | Sep 8 | Not started | Reusable for every future US event.
Cooler + ice + sanitary supplies | Game Day | Booth & Ops | 1 | 80 | 80 | Cash | Emma | HEB / local | Local (Emma) | Sep 11 | Not started | Chilled aloe demo + cold towels.
Booth misc (linens, tape, batteries, signage stands) | Game Day | Booth & Ops | 1 | 50 | 50 | Cash | Emma | Local | Local (Emma) | Sep 10 | Not started
NYC helper — assembly + delivery to FIT | NYC Pop | Labor | 1 | 220 | 220 | Cash | Brand Director | TaskRabbit / referral (hire by Aug 15) | — | Sep 9–10 work | Not hired | 1 day assembly + drop at FIT per Glossy load-in instructions. Different person from Emma.
Emma — Austin prep + event day | Game Day | Labor | 1 | 350 | 350 | Cash | Brand Director | Rehire (May event) | — | Sep 10–12 work | To confirm | Prep day (sticks, cards, kit assembly) + full event day.
Parcels & AWD removal fees → NYC | NYC Pop | Logistics | 1 | 100 | 100 | Cash | Head of Products | Amazon AWD + UPS/USPS | US only | Aug 22–28 | Not started | No international shipping. Handcarry (Sao & Eva) covers small/premium items only.
Austin local transport & stock moves | Game Day | Logistics | 1 | 50 | 50 | Cash | Emma | — | Local | Sep 10–12 | Not started | Austin house → campus load-in.
Creator gifting kits (existing merch) | Game Day | Booth & Ops | 6 | 0 | 0 | Existing stock | Brand Director | Austin house stock (rattan bags, scarves, fans) | Already in Austin | Sep 11 | Planned | $0 cash — rattan bags ×6, scarves, fans, brand books from existing stock.
Contingency reserve | Both | Contingency | 1 | 310 | 310 | Cash | Brand Director | — | — | — | Reserved | ~8% buffer for quote overruns / reprints / extra bags.
TOTAL (all rows incl. additions) |  |  |  |  | 3999

## Budget $4K
Budget Allocation — Total $4,000 (both events)
Estimated pulls live from Master Checklist (SUMIFS by Category). Allocations in blue are the plan — edit to reallocate; Remaining shows headroom.
| TOTAL BUDGET | 4000
Category | Allocated ($) | Estimated ($, live) | Remaining ($) | % of budget
Product | 1975 | 1975 | 0 | 49.38%
Packaging | 360 | 359 | 1 | 9%
Printing | 400 | 400 | 0 | 10%
Labor | 570 | 570 | 0 | 14.25%
Booth & Ops | 235 | 235 | 0 | 5.875%
Logistics | 150 | 150 | 0 | 3.75%
Contingency | 310 | 310 | 0 | 7.75%
TOTAL | 4000 | 3999 | 1 | 100%
View: cash out-of-pocket vs inventory
Cash out-of-pocket |  | 2024
Inventory COGS (from AWD stock) |  | 1975
Existing stock (zero cost) |  | 0
Note: if the BOD treats AWD product as inventory (not event cash), the cash ask is ~$2.0K of the $4.0K envelope.

## Event Ops
Event Operations — run-of-show & prep timeline
PREP TIMELINE (both events)
Week / Date | Milestone | Owner | Detail
W Jul 20 | Buyer lead-time answer — new miniset w/ loofah (GATE) | Buyer team | Decides Plan A vs Plan B for NYC bags. Must land NYC by Sep 4 to qualify.
W Jul 20 | Confirm bag count with Glossy (NYC) + booth specs with Dylan (Austin) | Brand Director | Bag qty drives product order; ask Glossy for load-in instructions at FIT.
W Jul 24 | Buyer confirms silk scarf qty (Austin creator kits) | Buyer team
W Jul 27 | Fortune texts written (~30) + ticket card design; voucher booklet design | Brand Director | Reuse brand templates; Western 'lucky ticket' layout.
W Aug 3 | Order: drawstring bags, voucher booklets; Klaviyo/Shopify codes (GLOSSYPOP / GAMEDAY tags) | Brand Director | Clone Endless Summer flow; unique codes if budget allows.
W Aug 10 | Hire NYC helper (by Aug 15); creators booked via Glossy roster | Brand Director | NYC helper ≠ Emma; brief with photo guide for assembly.
W Aug 17 | AWD removal orders placed (NYC 100+100, Austin 50) | Head of Products | Allow 1–2 weeks AWD processing + transit.
W Aug 24 | All NYC components at helper's address; test-assemble 1 bag, photo-approve | NYC helper | Checklist per bag: miniset (+aloe if Plan B), voucher booklet, brand book, tissue.
W Sep 1 | Austin print pickup; sticks numbered; Emma dry-run of fortune table | Emma
Sep 8–10 | Sao & Eva arrive (handcarry: brand books/premium small items); NYC bags assembled Sep 9–10 | All | Handcarry = US-entry personal luggage only, no intl freight.
Sep 10 | NYC: bags delivered to FIT per Glossy instructions | NYC helper | Get signed receipt + photos for report.
Sep 11 | Glossy Pop NYC (FIT) — bags distributed by Glossy; team is in Austin | Glossy | No staffing needed on site.
Sep 11 | Austin booth load-in prep + Emma brief + kit assembly | All | Per Dylan's load-in window.
Sep 12 | GAME DAY — booth from College GameDay morning through 6:30 PM kickoff | All | Run-of-show below.
Sep 13 | Debrief; content offload; voucher redemption tracking begins (thru Sep 30) | Brand Director
GAME DAY RUN-OF-SHOW — Sep 12, UT Austin
Time (CT) | Station / Activity | Who | Notes
07:30–09:00 | Load-in, booth build (panels, lanterns, fortune table, aloe cooler) | All 4 | Per Dylan's window; photos of build for content.
09:00–12:00 | College GameDay crowd — fortune draws open; founder 'come with me' reel | Emma (fortune) · Sao (content) | Content check-in every hour.
12:00–15:00 | Peak heat — chilled aloe demos + fans; creators visit booth | Eva (aloe) · Sao (creators) | Creators shoot at lantern corner; kits handed.
15:00–18:00 | Golden hour — lantern photo corner peak; hourly scarf draw | All | Best light for UGC; announce draws to hold crowd.
18:00–18:30 | Pre-kickoff push — last draws, aloe gifts for tagged posts | All | Cap check on aloe stock.
18:30+ | Teardown OR stay through game per Dylan's schedule | Emma + helper hands | Inventory count → report.
ROLES
Person | Role | Where | Notes
Sao | Founder face, creator hosting, content lead | Austin | Handcarry premium small items from VN.
Eva | Aloe station + ops support | Austin | Handcarry partner with Sao.
Emma | Fortune table, prep, logistics (Austin) | Austin | Rehired from May event.
NYC helper (hire by Aug 15) | Gift bag assembly + FIT delivery | NYC | Independent hire; photo-guided assembly brief.
Dylan (Glossy) | Booth PIC — specs, load-in, creator roster | Glossy | All booth design decisions confirmed with him.

## Marketing Capture
Marketing Capture Plan — make both events work online
TRACKING SETUP (before Aug 15)
Mechanism | How | Owner | KPI
Voucher codes — NYC | Booklet code(s) scoped + tagged 'glossypop' in Shopify; unique per booklet if print allows | Brand Director | Redemptions by Sep 30
Voucher QR — Game Day | Ticket-card QR → Klaviyo signup → single-use 15–20% code tagged 'gameday' | Brand Director | 250–400 emails; redemptions
UGC loop — Game Day | Draw quẻ → photo at lantern corner → post IG + tag @cobasdaughter → Aloe Gel gift | Emma enforces at booth | 60–80 tagged posts/stories
Hashtag & mentions | #cobasdaughter monitored during Sep 11–14; reshare best to stories | Brand team VN | Mentions lift vs Aug baseline
Amazon branded search | Watch branded-search trend Sep 12–30 (May event precedent: +327% w/ SB) | Head of Products | Branded search lift
CONTENT SHOT LIST — Game Day (owner: Sao)
Asset | Format | When | Destination
Founder 'come with me to game day' reel | IG reel 30–60s | Morning → dusk arc | IG + TikTok (150.7K-view format from June)
Booth build timelapse | Reel/story | 07:30–09:00 | Stories + report
Fortune draw reactions ×10+ | Short clips | All day | Ad engine (tracker1) + organic
Aloe relief POV ('watch them cool down') | Reel | Peak heat 12–15h | Ads + organic
Lantern corner golden-hour set | Photos + b-roll | 17–18:30 | Brand library + Q3 report
Creator visits + kit unboxings | Creator-owned | Scheduled slots | Whitelist best into Spark/Meta
NYC: bag assembly + FIT drop-off photos | Photos | Sep 9–10 | Recap post + BOD report
POST-EVENT (Sep 13–30)
Action | Detail | Owner | Due
Content offload → calendar | 40–60 clips → 4–6 weeks organic + ad engine | Brand team | Sep 15
Reshare + whitelist UGC | Best tagged posts → stories; top creators → Spark Ads | Brand team | Sep 20
Redemption + email report | glossypop / gameday code redemptions + Klaviyo list growth | Brand Director | Oct 2
Q3 report event section | Reuse May 'growth after the event' framing | Brand Director | Oct
Q4 gifting segue | Voucher validity ends Sep 30 → retarget into Q4 'Thoughtful Gifting' | Brand team | Oct